## Quality Report
Quality Report
Defect (No of Def/KLOC)
# | Product | Quality Control Activity | Plan | Actual
1 | Test
|  | Unit Test | 6-8
|  | Integration Test | 4-6 | 1
|  | System Test | 8-12 | 9
|  | Acceptance Test | 2-4 | 2
|  | Leakage (UAT) | 2-4 | 2
2 | Requirements | Review | 15 | 12
3 | Design | Review | 15 | 13
4 | Code | Review | 30 | 35
5 | Project Plan | Review | 7 | 3
6 | Project Schedule | Review | 10 | 6
7 | Test Plan | Review | 6 | 4
8 | Other document | Review | 15 | 13
Total |  |  | 120-132 | 100
Test Report
Refer to Test Report in TC Template