## Cover
Quality Management System
FAVN_Test Report
FAVN
Version : 1.0
Document Control information
Issue Date: | 17/11/2016
Issue Status: | Approved
Author: | Nguyễn Phúc An
Reviewer information | Đàm Huy Hùng | PM | Required
Approver information | Nguyễn Duy Anh | Member
Document Revision History
Date | Version | Description | Revised by
17/11/2016 | 1 | Create document | Đàm Huy Hùng
Note on B11: Add more reviewers as necessary
Note on B13: Add more approvers here as necessary

## Report
Test Report
Phase | # Test cases Planned | #Defects Planned | #Test cases Actual | #Defects Actual | % Tests Executed | % Tests Passed | % Tests Fail
Unit Test | 40TC/KLOC | 3 -4 defects/KLOC |  |  | 100% | 100% | 0%
Integration Test | 30TC/KLOC | 2 -3 defects/KLOC | 450 | 2 defects/KLOC | 100% | 100% | 0%
System Test | 20TC/KLOC | 4 -6 defects/KLOC | 636 | 8 defects/KLOC | 100% | 100% | 0%
Acceptance Test | N/A | 1-2 defects/KLOC | N/A | 2 defects/KLOC | 100% | 100% | 0%
Total | 90TC/KLOC | 10-15 defects/KLOC |  | 12 defects/KLOC | 100% | 100% | 0%
Phase | Round 1 |  |  |  | Round 2
| Pass | Fail | Untested | N/A | Pass | Fail | Untested | N/A
Unit Test | 61 | 0 | 0 | 0 | 61 | 0 | 0 | 0
Integration Test | 1090 | 40 | 4 | 0 | 1134 | 0 | 0 | 0
System Test | 52 | 20 | 4 | 0 | 74 | 0 | 0 | 0
Total | 1203 | 60 | 38 | 0 | 1269 | 0 | 0 | 0
Defect report
Defects | Logged | %Closed | %Invalid | %Open
Critical | 0 | 0% | 0% | 0%
High | 10 | 0% | 0% | 0%
Medium | 14 | 100% | 0% | 0%
Low | 20 | 100% | 0% | 0%
Total | 64 | 100% | 0% | 0%